## Sheet1
| MTV# | JobName | New/Existing | Type | JobRec | Job Mode | ConnectMode | Initial/Ongoing | Market/Cross | description | PurgefromDB | Mode | RunonDB | DevScrumCertification | FQCcert inFQCenv | Defect | FQCcert inSTLPLAB | Performance CertificationStatus | Certified by T1 in reporting mode | Validated by T1 in limited purge mode | Start to run in purge full population mode | PerfAnalysisWR | StartTime | ENDTime | Duration (inMin) | Volume | ReportingDB | SNEMock | Orderofdeployingtoproduction | Flag | Invoice/RIMImpact | OpenIssues | Status | SNEProdstatus | SNEMockstatus
Purge | MTV 2 | CSMINACTBPOP | New | Job | DLY_TNT_EVL | Population |  | On-going Purge | Market Level | Population identification job for Inactive BANs (Eligible Tentative BANs for Purge) | NA | Population | Customer | Yes | Yes |  | Yes | Completed |  |  |  | WR#4524971 | 2024-07-10 10:00 | 2024-07-10 10:01 | 0:00 | 685242 | [7 empty] | Completed | Completed
Purge | MTV 2 | CSMINACTBPRG | New | Daemon | CUST_ARCH_TNT | Purge Mode |  | On-going Purge | Market Level | Purge Job for Inactive BANs | TENTATIVE ARCH DB | Purge | Tentative Archive | Yes Certified with 2 - 4 BANs |  |  | Yes | Completed |  |  |  | WR#4550280 | 2024-09-09 08:22 | 2024-09-09 08:52 | 0:30 | 601 | [5 empty] | 2024-08-28 |  | Not Running | Not Started
Purge | MTV 2 | CSMINACTBPOP | New | Job | DLY_TNT_REP | Report Mode |  | On-going Purge | Market Level | text file will be created for list of BANs which are eligible for purge | TENTATIVE ARCH DB | Reporting Mode | Tentative Archive | Yes Certified with 2 - 4 BANs | Yes |  | Yes | Completed |  |  |  | WR#4540096 | 2024-08-12 06:28 | 2024-08-12 06:30 | 0:02 | 3268344 | [7 empty] | Completed | Completed
Purge | MTV 4 | CSMINACTBPOP | New | Job | DLY_CLSD_EVL | Population |  | On-going Purge | Market Level | Population of Closed BAN Archived DB | NA | Population | Customer | Yes | Yes |  | Yes | Completed |  |  |  | WR#4524971 | 2024-07-10 10:00 | 2024-07-10 10:01 | 0:00 | 84651 | [7 empty] | Completed | Completed
Purge | MTV4 | CSMINACTBPRG | New | Daemon | CUST_CLSB_PRG | Customer DB |  | On-goingPurge | MarketLevel | ResiduetoClosedBAN | CUSTOMERDB | Purge | Customer | Yes Certifiedwith2-4BANs | Yes |  | Yes | Completed |  |  |  | WR#4543902 | 8/29/20241:58:15AM | 8/29/20242:30:25AM | #VALUE! | 101 | [6 empty] | Performanceenhancementwillberequired | certified
Purge | MTV4 | CSMINACTBPRG | New | Daemon | CUST_ARCH_CLS | Closed BAN Archive DB |  | On-goingPurge | MarketLevel | PurgefromClosedBANarchiveDB | CLOSEDBANARCHDB | Purge | ClosedArchive | Yes Certifiedwith2-4BANs |  | WeneedIndexCRforSNEprod | yes | Completed |  |  |  | WR#4550280 | 9/9/20249:03:25AM | 9/9/20249:25:37AM | #VALUE! | 202 | [5 empty] | 4544588 |  | NotRunning | NotStarted
Purge | MTV 4 | CSMINACTBPRG | New | Daemon | HIST_CLSB_PRG | History Archive DB |  | On-going Purge | Market Level | Purge from History archive DB for closed BANs | HISTORY DB | Purge | History Archive | Yes Certified with 2 - 4 BANs |  |  | yes | In Progress 10/11/2024 |  |  |  | WR#4551884 | [9 empty] | 4545154/CDEX-350270/TLG-117719
Purge | MTV 4 | CSMINACTBPOP | New | Job | DLY_CLSD_REP | Report Mode |  | On-going Purge | Market Level | text file will be created for list of BANs which are eligible for purge | CLOSED BAN ARCH DB | Reporting Mode | Closed Archive | Yes Certified with 2 - 4 BANs |  |  | Yes | Completed |  |  |  | WR#4546106 | 2024-08-28 05:53 | 2024-08-28 06:11 | 0:19 | 5705325 | [7 empty] | Completed | Completed
LHR | MTV 5 | CSMBANLDLHR | New | Job | BY REQ | Load Job |  | On-going Purge | Market Level | Market level daily job will load the list of LH BANs coming as input file from external system in an intermediate table. | CLOSED BAN LHR DB | Population | Closed LHR | NO |  | need to run in SNE Mock | Yes | Completed |  |  |  | WR#4542688 | 2024-08-22 05:28 | 2024-08-22 05:29 | 0:01 | 10 | [5 empty] | 2024-08-20 |  | certified
LHR | MTV 5 | CSMPRGLHR | New | Daemon | CLS_LHR_PRG | Purge Mode |  | On-going Purge | Market Level | The daemon will purge the non-LH data and BAN data for non-LH BANs and non-LH data for LH BANs. | CLOSED BAN LHR DB | Purge | Closed LHR | NO |  |  | In progress 10/20 | Pending 10/24/2024 | [13 empty] | 4542152
LHR | MTV 5 | CSARCHIVE | Existing | Job | ARCHMEMO | Archiving job |  | On-going Purge | Market Level | The existing archive job,”CSARCHIVE” that moves the data from customer DB to Closed BAN Archive DB will be enhanced to additionally record the details of the closed BANs that have been archived in the current run in a new table ”CLOSE_BAN_ARCH” in Closed BAN Archive DB. | CLOSED BAN LHR DB | Archiving Job | Customer | NO | pending |  | yes | Completed |  |  |  | WR#4547627 | 2024-09-11 13:27 | 2024-09-11 15:52 | 2:26 | 15467952 | [5 empty] | WR 4539039
LHR | MTV 5 | CSMCPYCLSBARC | New | Job | CLSB_LHR_PRG | copy Job |  | On-going Purge | Market Level | This batch job will process the pending records from new table “CLOSE_BAN_ARCH” and will copy the BAN data from Closed BAN Archive DB to Closed BAN LHR DB. Once the BAN data is copied to LHR DB, the job will update the status in “CLOSE_BAN_ARCH” from "Pending" to "Processed" status. | CLOSED BAN LHR DB | CopyCLOSED BAN Job | Closed Archive | NO |  |  | CDEX-352531 | In Progress 10/11/2024 |  |  |  | WR#4550523 | [8 empty] | Impacted | 4547625 | After CSarchive job enhancement is success we will be able to test thisjob
Purge | MTV 6 | CSMINACTBPRG | New | Daemon | CUST_INACT_PRG | T |  | On-going Purge | Market Level | This will connect to Customer DB to get the source tables and purge from Customer DB. It will also update the purge status in “RIM_INACT_PURGE_ELIG_BAN” for the BAN in Customer DB. The secondary connection will be using TLG_CONNECT_IND as “F”. | CUSTOMER DB | Purge | Customer | Yes Certified with 2 - 4 BANs | Yes |  | Yes | Completed |  |  |  | WR#4546483 | 2024-08-29 02:12 | 2024-08-29 02:23 | 0:10 | 101 | [7 empty] | certified | Not Started
Purge | MTV7 | CSMINACTBPRG | New | Daemon | CUST_CLSB_PRG | C |  | On-goingPurge | MarketLevel | ThiswillconnecttoCustomerDBtogetthesourcetablesandpurgefromCustomerDB.Itwillalsoupdatethepurgestatusin“RIM_INACT_PURGE_ELIG_BAN”fortheBANinCustomerDB.ThesecondaryconnectionwillbeusingTLG_CONNECT_INDas“F”. | CUSTOMERDB | Purge | Customer | Yes Certifiedwith2-4BANs | Yes |  | Yes | Completed |  |  |  | WR#4543902 | 2024-08-29 01:58 | 2024-08-29 02:30 | 0:32 | 101 | [7 empty] | certified | NotStarted
LHR | MTV 10 | CSMPRGLHR | New | Daemon | HIST_LHR_PRG |  |  | On-going Purge | Market Level | This will connect to Customer LHR DB to get the source tables and purge the data from History BAN LHR DB. The secondary connection will be using TLG_CONNECT_IND as “M”. | HISTORY LHR DB | Purge | History LHR | NO |  |  | In progress 10/20 | Pending 10/24/2024 | [13 empty] | 4542152(ETA : 3 Sept) |  |  | Not Started
LHR | MTV 20 | CSMPRGLHR | New | Daemon | CUST_LHR_PRG |  |  | On-going Purge | Market Level | This will connect to Customer LHR DB to get the source tables and purge the data from CUSTOMER LHR DB. The secondary connection will be using TLG_CONNECT_IND as “K”. | CUSTOMER LHR DB | Purge | Customer LHR | NO |  |  | In progress 10/20 | Pending 10/24/2024 | [16 empty] | Not Started
Purge | MTV 12 | CSMFINPOP | New | Job | POPFIN |  |  | On-going Purge | Market Level | Job will build population Indentification according to the RIM criteria. | CUSTOMER DB | Population | Customer | Yes(Completed in STL, Performance Issue in NBI(temp space)) |  |  | Yes | Completed |  |  |  | WR#4546221 | 2024-08-28 05:26 | 2024-08-28 07:25 | 1:59 | 168061563 | • Next step: test in NBI PLAB. ECR for 2408 is needed for fixes • Putting this in prod will wait until 2408 • @Gaurav Srivastava we need to run them in SNE mock & reporting. |  |  |  | Impacted | 2024-08-16 |  | Completed | started
Purge | MTV 12 | CSMFINPRG | New | Daemon | BAN_BILL_PRG |  |  | On-going Purge | Market Level | Will purge records from the candidate tables related to BILL_SEQ_NO tables | CUSTOMER DB | Purge | Customer | Yes Certified with 2 - 4 BANs (Performance Issue) | pending |  | Yes | In Progress 10/20/2024 |  |  |  | WR#4545799 | 2024-08-22 06:38 | 2024-08-22 06:55 | 0:17 | [6 empty] | 4548004/4545799 | Delete is running long , Perf analysis required
Purge | MTV 12 | CSMFINPRG | New | Daemon | BAN_INV_PRG |  |  | On-going Purge | Market Level | Will purge records from the candidate tables related to INVOICE_SEQ_NO tables | CUSTOMER DB | Purge | Customer | Yes Certified with 2 - 4 BANs (Performance Issue) | pending from Dev - 7/16 |  | WR raised | In Progress 10/20/2024 |  |  |  | WR#4545799 | [8 empty] | Impacted | 4546109(ETA : 5 Sept)
Purge | MTV 12 | CSMFINPRG | New | Daemon | BAN_INST_PRG |  |  | On-going Purge | Market Level | Will purge records from the candidate tables related to INST_SEQ_NO tables | CUSTOMER DB | Purge | Customer | Yes Certified with 2 - 4 BANs (Performance Issue) | pending |  | CDEX-351035 | In Progress 10/20/2024 |  |  |  | WR#4545799 | [9 empty] | 4546108 | PF provided By dev , in retest(9/25 p2p)
Purge | MTV 18 | CSMODSPURGE | New | Daemon | CUSTACT |  |  | On-going Purge | Market Level | this Job rec will Purge the GL tables of MTV 18 | CUSTOMER DB | Purge | Customer | Yes Certified with 2 - 4 BANs | Yes |  | Yes | In Progress 10/07/2024 |  |  |  | WR#4546104 | 2024-08-28 05:39 | 2024-08-28 05:53 | 0:14 | [8 empty] | Not Running | Started
Purge | MTV 16 | CSMODSPURGE | New | Daemon | CUSTACT |  |  | On-going Purge | Market Level | this Job rec will purge all active BANs from CSM Tables listed in MTV 16 | CUSTOMER DB | Purge | Customer | Yes Certified with 2 - 4 BANs | Yes |  | TLG-117769 | In Progress 10/07/2024 |  |  |  | WR#4546104 | 2024-08-28 05:39 | 2024-08-28 05:53 | 0:14 | [6 empty] | WR 4536239(ETA : 3 Sept) | PF provided By dev , in retest(9/25 p2p) |  | Started
Purge | MTV 16 | CSMODSPURGE | New | Daemon | HISTACTARC |  |  | On-going Purge | Market Level | this job rec will purge all active BANs from 11 table history archive DB tables listed in MTV16F1US3 | HISTORY DB | Purge | History Archive | Yes Certified with 2 - 4 BANs |  |  | Yes | In Progress 10/17/2024 |  |  |  | WR#4551860 | [9 empty] | 4546969(CDEX-350645) TLG-117719
Purge | MTV 21 | CSMODSPURGE | New | Daemon | MCM_SEC_PRG |  |  | On-going Purge | Market Level | This will connect to MCMSEC-DB DB to get the source tables and purge it. The secondary connection will be using TLG_CONNECT_IND as “X”. | CROSS MARKET SECURITY DB | Purge | Security MCM | NO | pending | do not run in prod until end of project | Yes | Completed |  |  |  | WR#4551481 | 2024-09-10 02:53 | 2024-09-10 02:54 | 0:00 | 20000 | [5 empty] | WR 4540480 |  | Not Started | Not Started
Purge | MTV 21 | CSMODSPURGE | New | Daemon | MKT_SEC_PRG |  |  | On-going Purge | Market Level | This will connect to MarketSecurity DB to get the source tables and purge it. The secondary connection will be using TLG_CONNECT_IND as “Y”. | MARKET LEVEL SECURITY DB | Purge | Security Market | NO | pending |  | Yes | In Progress 10/11/2024 |  |  |  | WR#4542291 | 2024-08-29 01:52 | 2024-08-29 01:52 | 0:00 | [6 empty] | 2024-08-28 |  | Not Started | Not Started
Purge | MTV 22 | CSMODSPURGE | New | Daemon | MKB_CROSS_PRG |  |  | On-going Purge | Market Level | This will connect to MKB DB to get the source tables and purge it. The secondary connection will be using TLG_CONNECT_IND as “Z”. | MKB DB | Purge | MKB | NO | pending | do not run in prod until end of project | Yes | Completed |  |  |  | WR#4551481 | 2024-09-11 07:03 | 2024-09-11 07:05 | 0:02 | 30000 | [5 empty] | CDEX-346092 |  | Not Started | Cannot Run in Mock
Purge | MTV 22 | CSMODSPURGE | New | Daemon | USAGE_PRG |  |  | On-going Purge | Market Level | This will connect to Usage DB to get the source tables and purge it. The secondary connection will be using TLG_CONNECT_IND as “U”. | USAGE DB | Purge | Usage | NO | pending | need to run in SNE Mock | Yes | Completed |  |  |  | WR#4540090 | 2024-09-02 08:04 | 2024-09-02 08:04 | 0:00 | 144 | [5 empty] | 2024-08-28 |  | certified | Need to Run by MAF Team
Purge | MTV 24 | CSMODSPURGE | New | Daemon | CUSTACT |  |  | On-going Purge | Market Level | this will covered non-PK tables | CUSTOMER DB | Purge | Customer | Yes Certified with 2 - 4 BANs | Yes |  | Yes | In Progress 10/07/2024 |  |  |  | WR#4546104 | 2024-08-28 05:39 | 2024-08-28 05:53 | 0:14 | [6 empty] | 2024-08-28 |  |  | Started
Purge | MTV 14 | CSMODSPURGE | New | Daemon | CUSTACT |  |  | On-going Purge | Market Level | this Job rec will Purge the AR tables of MTV 14 | CUSTOMER DB | Purge | Customer | Yes Certified with 2 - 4 BANs | Yes |  | Yes | In Progress 10/07/2024 |  |  |  | WR#4546104 | 2024-08-28 05:39 | 2024-08-28 05:53 | 0:14 | [6 empty] | 2024-08-28 |  |  | Started
Purge | MTV 25 | CSMODSPURGE | New | Daemon | INTCSMPRG |  |  | On-going Purge | Market Level | this will purge Internal Tables from Customer DB | CUSTOMER DB | Purge | Customer | Yes Certified with 2 - 4 BANs | Yes |  | Yes | Completed |  |  |  | WR#4538257 | 2024-08-14 02:41 | 2024-08-14 02:42 | 0:01 | 2706 | [5 empty] | 2024-08-28 |  | certified
Purge | MTV 25 | CSMODSPURGE | New | Daemon | INTNCIPRG |  |  | On-going Purge | Market Level | this will purge Internal Tables from NCI DB | NCI DB | Purge | NCI | NO | pending | do not run in prod until end of project | Yes | Completed |  |  |  | WR#4546547 | 2024-08-29 02:46 | 2024-08-29 02:46 | 0:00 | 19963 | [7 empty] | certified
Purge | MTV 25 | CSMODSPURGE | New | Daemon | INTWNPPRG |  |  | On-going Purge | Market Level | this will purge Internal Tables from WNP DB | WNP DB | Purge | WNP | NO | pending |  | CDEX-352533 | Pending 10/24/2024 | [13 empty] | 4550577
Purge | MTV 25 | CSMODSPURGE | New | Daemon | INTMKBPRG |  |  | On-going Purge | Market Level | this will purge Internal Tables from MKB DB | MKB DB | Purge | MKB | NO | pending | do not run in prod until end of project | Yes | Completed |  |  |  | WR#4546547 | 2024-08-21 05:51 | 2024-08-21 05:52 | 0:01 | 1000
Purge | MTV 25 | CSMODSPURGE | New | Daemon | INTMAFPRG |  |  | On-going Purge | Market Level | this will purge Internal Tables from MAF DB | MAF DB | Purge | MAF | NO | pending |  | WR raised | Completed |  |  |  | WR#4546547 | 2024-08-21 09:32 | 2024-08-21 09:33 | 0:01 | 15 | [5 empty] | 4547954/4550581
Purge | MTV 26 | CSMINACTBPRG | New | Daemon | CUST_INACT_PRG | Tentative Archived DB tables |  | On-going Purge | Market Level | This will connect to Customer DB to get the source tables and purge from Customer DB. It will also update the purge status in “RIM_INACT_PURGE_ELIG_BAN” for the BAN in Customer DB. The secondary connection will be using TLG_CONNECT_IND as “F”. | CUSTOMER DB | Purge | Customer | Yes Certified with 2 - 4 BANs | Yes |  | Yes | Completed |  |  |  | WR#4546483 | 2024-08-29 02:12 | 2024-08-29 02:23 | 0:10 | 101 | [7 empty] | certified
Purge | MTV26 | CSMINACTBPRG | New | Daemon | CUST_CLSB_PRG | Closed BAN Archive DB tables |  | On-goingPurge | MarketLevel | ThiswillconnecttoCustomerDBtogetthesourcetablesandpurgefromCustomerDB.Itwillalsoupdatethepurgestatusin“RIM_INACT_PURGE_ELIG_BAN”fortheBANinCustomerDB.ThesecondaryconnectionwillbeusingTLG_CONNECT_INDas“F”. | CUSTOMERDB | Purge | Customer | Yes Certifiedwith2-4BANs | Yes |  | Yes | Completed |  |  |  | WR#4543902 | 2024-08-29 01:58 | 2024-08-29 02:30 | 0:32 | 101 | [5 empty] | 2024-08-28 |  | certified
Purge | MTV 27 | CSMODSPURGE | new | Daemon | CSMODSREP | Active BANs for MTV16 |  | On-going Purge | Market Level | this Job will identify data eligible for purge for all active BANs from each table for which purge date column is lesser than the RIM date range. (MTV 16) | CUSTOMER DB | Reporting Mode | Customer | Yes(NBI) | pending |  | Yes | Completed |  |  |  | WR#4539073 | 2024-08-14 06:24 | 2024-08-14 08:11 | 1:47 | 1000 | [7 empty] | Completed | Completed
Purge | MTV 27 | CSMFINPRG | New | Daemon | FINREP | Active BANs for MTV11-18 |  | On-going Purge | Market Level | this Job will identify data eligible for purge for all active BANs from each group / Individual tables for which purge date column is lesser than the RIM date range. (MTV 11-18) | CUSTOMER DB | Reporting Mode | Customer | In progress (NBI) | fix delivered. Need ECR TLG-117300 Marina Murphy FIN ECR. This fix is for 2408. Private fix can be provided for 2406. @Atul Kumar will check | WR #4548020 - FIX pending for SNE | 16-Aug (Certifiedin FQC) | In Progress 10/11/2024 |  |  |  | WR#4537784 | 2024-08-12 05:50 | 2024-08-12 12:37 | 6:47 |  | • Next step: test in NBI PLAB. ECR for 2408 is needed for fixes • Putting this in prod will wait until 2408 • @Gaurav Srivastava we need to run them in SNE mock & reporting. |  |  |  | Impacted | WR #4531657)(CDEX-334610 |  | Completed | started
Purge | MTV 27 | CSMODSPURGE | New | Daemon | REP_MCMSEC_PRG | MTV 21.F1.US2 |  | On-going Purge | Cross Market | This will connect to the MCMSEC-DB DB to get the source tables and report. | CROSS MARKET SECURITY DB | Reporting Mode | Security MCM | Yes(NBI) | pending | do not run in prod until end of project | yes | Completed |  |  |  | WR#4542774 | 2024-08-23 00:51 | 2024-08-23 02:44 | 1:52 | 435828 |  | cannot tets in Mock
Purge | MTV 27 | CSMODSPURGE | New | Daemon | REP_SEC_PRG | MTV 21.F2.US2 |  | On-going Purge | Market Level | This will connect to MarketSecurity DB to get the source tables and purge it. | MARKET LEVEL SECURITY DB | Reporting Mode | Security | Yes(NBI) | pending | need to run in SNE Mock | Yes | Completed |  |  |  | WR#4540107 | 2024-08-20 07:05 | 2024-08-20 07:06 | 0:01 | 305993 |  | can test in Mock | [5 empty] | certified | Completed
Purge | MTV 27 | CSMODSPURGE | New | Daemon | REP_MKB_PRG | MTV 22.F1.US2 |  | On-going Purge | Market Level | This will connect to the MKB DB to get the source tables and report it. | MKB DB | Reporting Mode | MKB | Yes(NBI) | pending | do not run in prod until end of project | Yes | Completed |  |  |  | WR#4540107 | 2024-08-14 01:00 | 2024-08-14 01:56 | 0:56 | 14800000 |  | cannot tets in Mock | [5 empty] | Not Started | Cannot Run in Mock
Purge | MTV 27 | CSMODSPURGE | New | Daemon | REP_USG_PRG | MTV 22.F2.US2 |  | On-going Purge | Market Level | This will connect to Usage DB to get the source tables and report it. | USAGE DB | Reporting Mode | Usage | Yes(NBI) | pending | need to run in SNE Mock | Yes | Completed |  |  |  | WR#4540107 | 2024-08-16 02:36 | 2024-08-16 02:39 | 0:02 | 1968272 |  | can test in Mock | [5 empty] | certified
Purge | MTV 27 | CSMODSPURGE | New | Daemon | CSMODSREP | MTV24 |  | On-going Purge | Market Level | this will Report CSM Tables | CUSTOMER DB | Reporting Mode | Customer | Yes(NBI) | pending |  | Yes | Completed |  |  |  | WR#4539073 | 2024-08-14 06:24 | 2024-08-14 08:11 | 1:47 | 1000 | MTZ validation completed | [6 empty] | Completed | Completed
Purge | MTV 27 | CSMODSPURGE | New | Daemon | INTCSMREP | MTV25 |  | On-going Purge | Market Level | this will Report Internal Tables from Customer DB | CUSTOMER DB | Reporting Mode | Customer | Yes(NBI) | pending |  | Yes | Completed |  |  |  | WR#4538257 | 2024-08-21 10:00 | 2024-08-21 10:05 | 0:06 | 5000 | MTZ validation completed | [6 empty] | Completed | Completed
Purge | MTV28 | CSCOMPREP | New | Job | INACT_ARC_REP | MTV 28 |  | On-going Purge | Market Level | This new JOB REC “INACT_ARC_REP” will be added to the new job “CSCOMPREP” to handle compliance reporting for Closed BAN Archive DB. | CLOSED BAN ARCH DB TENTATIVE BAN ARCH DB | Compliance Reporting | Closed Archive DB Tent Archive DB | NO |  |  | Yes | In Progress 10/11/2024 |  |  |  | WR#4542620 | 2024-08-21 10:45 | 2024-08-21 10:46 | 0:01 | [6 empty] | 2024-08-28
Purge | MTV28 | CSCOMPREP | New | Job | HIS_ARC_REP | MTV 28 |  | On-going Purge | Market Level | this new JOB REC “HIS_ARC_REP” will be added to the new job “CSCOMPREP” to handle compliance reporting for History Archive DB | HISTORY DB | Compliance Reporting | History Archive | NO |  |  | Yes | Completed |  |  |  | WR#4558088 | 2024-09-30 05:06 | 2024-09-30 05:12 | 0:05 | 227840525 | [5 empty] | 2024-08-28
Purge | MTV28 | CSCOMPREP | New | Job | CUS_PRG_REP | MTV 28 |  | On-going Purge | Market Level | This new JOB REC “CUS_PRG_REP” will be added to the new job “CSCOMPREP” to handle compliance reporting for Customer DB | CUSTOMER DB | Compliance Reporting | Customer | NO | pending |  | In progress 10/20 | In Progress 10/20/2024 |  |  |  | WR#4542620
Purge | MTV28 | CSCOMPREP | New | Job | MKB_PRG_REP | MTV 28 |  | On-going Purge | Market Level | This new JOB REC “MKB_PRG_REP” will be added to the job “CSCOMPREP” to handle compliance reporting for MKB DB | MKB DB | Compliance Reporting | MKB | NO | pending | do not run in prod until end of project | Yes | Completed |  |  |  | WR#4558088 | 2024-09-30 05:05 | 2024-09-30 05:06 | 0:02 | 191952904 | [5 empty] | 2024-08-28
Purge | MTV28 | CSCOMPREP | New | Job | USG_PRG_REP | MTV 28 |  | On-going Purge | Market Level | This new JOB REC “USG_PRG_REP” will be added to the job “CSCOMPREP” to handle compliance reporting for Usage DB | USAGE DB | Compliance Reporting | Usage | NO | pending |  | Yes | Completed |  |  |  | WR#4558088 | 2024-09-30 05:00 | 2024-09-30 05:00 | 0:00 | 1968433 | [5 empty] | 2024-08-28
Purge | MTV28 | CSCOMPREP | New | Job | MSEC_PRG_REP | MTV 28 |  | On-going Purge | Market Level | This new JOB REC “MSEC_PRG_REP” will be added to the job “CSCOMPREP” to handle compliance reporting for Security DB | MARKET LEVEL SECURITY DB | Compliance Reporting | Security Market | NO | pending |  | Yes | Completed |  |  |  | WR#4558088 | 2024-09-30 03:55 | 2024-09-30 03:55 | 0:00 | 597395
Purge | MTV28 | CSCOMPREP | New | Job | CSEC_PRG_REP | MTV 28 |  | On-going Purge | Cross Market | This new JOB REC “CSEC_PRG_REP” will be added to the job “CSCOMPREP” to handle compliance reporting for Cross Market Security DB | CROSS MARKET SECURITY DB | Compliance Reporting | Security MCM | NO | pending | do not run in prod until end of project | Yes | completed |  |  |  | WR#4558640 | 2024-10-01 01:12 | 2024-10-01 01:13 | 0:00 | 124319414
Purge | MTV28 | CSMLHRREP | New | Job | CLS_LHR_REP | MTV 28 |  | On-going Purge | Market Level | This new JOB REC “CLS_LHR_REP” will be added to the job “CSMLHRREP” to handle compliance reporting for Closed LHR Archive DB. | CLOSED BAN LHR DB | Compliance Reporting | Closed LHR | NO |  |  | CDEX-351031 | In Progress 10/20/2024 |  |  |  | WR#4550589 | [8 empty] | Impacted | 4546979 (ETA 4 Sep) | PF fix provided by dev(9/25 p2p)
Purge | MTV28 | CSMLHRREP | New | Job | HIS_LHR_REP | MTV 28 |  | On-going Purge | Market Level | This new JOB REC “HIS_LHR_REP” will be added to the job “CSMLHRREP” to handle compliance reporting for History Archive LHR DB. | HISTORY LHR DB | Compliance Reporting | History LHR | NO |  |  | CDEX-351028 | In Progress 10/20/2024 |  |  |  | WR#4550589 | [8 empty] | Impacted | 4546983(ETA 4 Sep) | PF fix provided by dev in retest(9/25 p2p)
Purge | MTV28 | CSMLHRREP | New | Job | CUS_LHR_REP | MTV 28 |  | On-going Purge | Market Level | This new JOB REC “CUS_LHR_REP” will be added to the job “CSMLHRREP” to handle compliance reporting for Customer LHR DB | CUSTOMER LHR DB | Compliance Reporting | Customer LHR | NO |  |  | CDEX-348679 | In Progress 10/20/2024 |  |  |  | WR#4550589 | [8 empty] | Impacted | 4543477/CDEX-348679
Purge | MTV16 | GNDBACLEANUP | Existing | Job | ARCH 01-09 |  |  |  | Market Level | Existing job which archives data from customer |  | Archiving Job | Customer | Yes | pending |  | Yes | Completed |  |  |  | WR#4537790 | 2024-08-09 08:21 | 2024-08-09 13:15 | 4:54 | 7646321 | [5 empty] | 2024-08-28 | Completed
[23 empty] | 2024-08-12 04:29 | 2024-08-12 06:58 | 2:29 | 1822618
[23 empty] | 2024-08-12 07:11 | 2024-08-12 09:16 | 2:05 | 1797348
LHR | MTV16 | CSMCPHSTARC | New | Job | COPYHIST |  |  |  | Market Level | New job to copy data from history archive to history LHR | NA | Copy Job | History LHR | No |  |  | CDEX-352532 | In Progress 10/11/2024 |  |  |  | WR#4548447 | [9 empty] | WR 4542152
Purge | MTV19 | BFBLIMGPOP | New | Job | EOD / BYREQ |  |  | On-going Purge | Market Level | This New Job will populate Eligible Bill details for the purge. | CUSTOMER DB | Population | Customer | NO | pending |  | CDEX-351456 | Pending 10/20/2024 | [13 empty] | WR4533131 | date util error now
Purge | MTV19 | BFBLIMGPRG | New | Job | EOD / BYREQ |  |  | On-going Purge | Market Level | This New Job will purge the physical Bill file from the respective DB and Market | CUSTOMER DB | Purge | Customer | NO | pending |  | CDEX-351456 | Pending 10/24/2024 | [13 empty] | WR4533131